HPAB MEETING MINUTES –DECEMBER 16, 2010

Attending:  Nancy Arcieri, Vic Bary,  Lori Hoffner, Ron Meeks, Loretta Smith, Maureen Strazdon, Mary Wilford, Carolyn Youngs

Priority Activities

North Cranford Historical District

- Maureen reported that the preliminary proposal was distributed to Township, and the presentation to Township Committee was postponed from December 13 – no new date given

- Kinney has created a database on streets on Googledocs (https://docs.google.com/?authuser=0#folders-shared-with-me)

- Vic has taken photos of all 525 houses

- Maureen met with and included comments from Bob Hudek who suggested draft ordinances not be included

- By January 10

  - write descriptions of the 525 houses – Nancy, Vic, Kinney, Ron, Maureen – Vic has started and can provide help

  - send talking points and all documents to group - Maureen

  - discuss final draft with Dan Ashenbach (Carolyn and Mary), Dave Robinson ( Lori), Mark Dugan (Maureen), Kevin Illing (Maureen), Bob Puhak (Maureen), Ed O'Malley (Carolyn), Kevin Campbell (Carolyn)

  - put final draft proposals on preservecranford.com - Bill

- compare NCHD vs what we have in individual house database so that we can include house description sheets

HPAB Information to residents and Township

- Bill needs to update Preservecranford.com

- Maureen will resubmit the article on NCHD to Cranford Patch near Township meeting date

Other projects

Membership

  - Maureen notified Tara Rowley that all current members want to continue

- Nancy contacted Larry Fuhro on Nov 2 re student member; Maureen followed up in Dec, Maureen will send a letter to the HS and check book in HS guidance office to identify student member

Articles on Character of Cranford

- Jean working on 22 Forest

Fireplace preservation

- Maureen reported no word on where the fireplace will go until after Jan 1

- Maureen contacted of L'esperance Tile Works, Motawi,and Pewabic on 11/28 re repro tiles – no response

- Maureen will re-check with Union County about how fund-raising must be done

A Cruise Through Cranford’s Architecture – Video

- Ron submitted notes for script update

Sign posts

- Maureen to write article

Walking tours

- Patrick Lynch’s and Ricky Barry’s South Side tour to Bill for preservecranford

- Loretta showed information and pictures of houses/sketches of models in Sunny Acres – doing a tour for the Spring 70th Anniversary of the Association celebration

The next HPAB meetings will be on Thursday, January 27, February 24, and March 24 at the Community Center at 7:30.